## Overview
PurpleTech
Team Members
First Name | Last Name | ID | Program | Initials
Allaye | Dicko | 40224071 | SOEN | AD
Shah | Murshed | 40176037 | COEN | SM
Oyeyimika | Adeoye | 40124538 | COEN | OA
Huy | Minh Le | 40209514 | COEN | HM
Sadee | Shadman | 40236919 | SOEN | SS
Grecia | O'Brien | 25372232 | SOEN | GO
ORGANIZATION STRUCTURE OF THIS SPREAD SHEET: |  |  |  |  | structure may alter as the course progresses and we see some aspect of the project require it's own category
Pre-Start: • Outlines any tasks or activities undertaken • May include training, early research etc. Sprint • Records activities conducted during the milestone.

## Allaye
Allaye's LOG
ID: 40224071
PROGRAM: SOEN
PREP PHASE
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
2023-11-11 | Meeting | Everyone | Sprint 4 planning | Talked about the plan for Sprint 4 and task breakdown | 1.5
SPRINT 4
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
2023-11-13 | Development | Myself | House comparator Integration | Integrated new house comparator feature into the final application and ensured functionality | 2.5
2023-11-15 | Development | Myself | Bug fixes | Added missing functionality and refactored code and labels, pushed final demo to github and had all members review | 3
2023-11-16 | meeting | Everyone | Feature Embedding + Presentation preparation | Embedded all of our features to the website and prepared our powerpoint presentation | 1
2023-11-26 | meeting | Everyone | Project finalization | Discussed overall github organization, made sure all issues were completed and the project was functioning as planned | 1

## Oyeyimika
Oyeyimika's LOG
ID: 40124538
PROGRAM:COEN
PREP PHASE
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT | TEAM'S SIGNATURE
[6 empty] | Allaye | Shah | Oyeyimika | Min | Sadee | Grecia
2023-11-11 | Meeting | Team | Sprint 4 planning | Talked about the plan for Sprint 4 and task breakdown | 1.5
SPRINT 4
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT | TEAM'S SIGNATURE
[6 empty] | Allaye | Shah | Oyeyimika | Min | Sadee | Grecia
2023-11-13 | Implementation | Individually | Coding and implementing extra feautures such as price filters, area per sq ft. | Implemented more filters, and a .csv file to store the data collected. | 2.5
2021-11-21 | Meeting | Team | Discussion on Sprint 4 tasks, new information on presentation/report | Discussed presentation/project information provided by the professor, discussions on sonarqube, testings & documentation | 0.5
2023-11-25 | Meeting | Team | Follow up on task for Sprint 4 | Continued discussion from the last meeting and set action plans in motion. | 0.5
2023-11-26 | Documentation | Individually | Documenting Meeting Minutes, Creating Issues, Blogs, Peer review | Completed documentations and pushed to github | 3
2023-11-26 | Meeting | Team | Project finalization | Discussed overall github organization, made sure all issues were completed and the project was functioning as planned Feature Embedding + Presentation preparation | 1.5

## Minh
Minh's LOG
ID: 40209514
PROGRAM: COEN
PREP PHASE
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
SPRINT 4
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
2023-11-15 | coding | me | work on adding a nav bar on each page | new and nice navigation bar for each tab | 2
2023-11-25 | meeting | Shah Yimika Sadee Grecia Minh | planning sprint 4 | distributing the task | 0.5
2023-11-25 | coding | me | implementing new colors | the tabs are now redesign | 1
2023-11-26 | meeting | everyone | planning presentation and final report | task have been distributed | 2
2023-11-26 | coding | me | finalizing front end and embed the new features | finalizing front end and embed the new features | 3

## Sadee
Sadee's LOG
ID: 40236919
PROGRAM: SOEN
PREP PHASE
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
2023-11-11 | Meeting | Everyone | Sprint 4 planning | Talked about the plan for Sprint 4 and task breakdown | 1.5
SPRINT 4
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
2021-11-21 | Meeting | Team | Discussion on Sprint 4 tasks, new information on presentation/report | Discussed presentation/project information provided by the professor, discussions on sonarqube, testings & documentation | 0.5
2023-11-25 | Meeting | Team | Follow up on task for Sprint 4 | Continued discussion from the last meeting and set action plans in motion. | 0.5
2023-11-25 | Coding | Myself | Implementing the Offer Management Feature. Creating accept and reject button aas well as their functionality. | Pushed into github. Offer management working properly as required on the rubric. | 6 hours
2023-11-25 | Documentation | Myslef | Acceptance Tests (AT) (all of them written and finalized on this sprint) | Written all acceptance tests and linked them to User Story-Tasks. All acceptance tests for the 8 user stroeis are written and checked. Everything is avaialble is available in the wiki. | 1
2023-11-26 | Meeting | Everyone | Project finalization | Discussed overall github organization, made sure all issues were completed and the project was functioning as planned Feature Embedding + Presentation preparation | 1.5

## Grecia
Grecia's LOG
ID: 25372232
PROGRAM: SOEN
PREP PHASE
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
2023-06-11 | Meeting | Everyone | Sprint 4 Planning | Discussed sprint planning and task breakdown | 1.5
SPRINT 4
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
16/11/2023 | Implementation | Myself | Modify Calculator Logic for the Mortage Calculator (see output for full description including rationale, code, code explanation, and GUI) | https://github.com/purpletechceo/purpletech-soen341projectF2023/issues/88 | 1
16/11/2023 | Implementation | Myself | Build Payment Schedule for the Mortgage Calculator (see output for full description including rationale, code, code explanation, and GUI) | https://github.com/purpletechceo/purpletech-soen341projectF2023/issues/89 | 1
16/11/2023 | Implementation | Myself | Build Amortization Schedule for the Mortgage Calculator (see output for full description including rationale, code, code explanation, and GUI) | https://github.com/purpletechceo/purpletech-soen341projectF2023/issues/90 | 2
16/11/2023 | Implementation | Myself | Implement Summary Dashboard for the Mortgage Calculator (see output for full description including rationale, code, code explanation, and GUI) | https://github.com/purpletechceo/purpletech-soen341projectF2023/issues/91 | 2
16/11/2023 | Implementation | Myself | Scenario Analyzer for Loan Term Comparison for the Mortgage Calculator (see output for full description including rationale, code, code explanation, and GUI) | https://github.com/purpletechceo/purpletech-soen341projectF2023/issues/92 | 2
16/11/2023 | User Acceptance Testing | Myself | Wrote the Use Acceptance Tests for Mortgage Calculator, including 8 scenarios using the GIVEN, WHEN, THEN methodology | https://github.com/purpletechceo/purpletech-soen341projectF2023/issues/93 | 1.5
16/11/2023 | Unit Test | Myself | Created Unit Test (Matching the Scenarios Above) | test_mortgageCalculator.py | 1.5
16/11/2023 | Meeting | Everyone | Presentation Preparation | Worked on all the Lessons Learned and Conclusion slides https://liveconcordia-my.sharepoint.com/:p:/g/personal/a_dicko_live_concordia_ca/EdNcecLv3ZBJoPRFStsQsX4B940z5rSSdh-aZ83IIgP8jg?e=OOtD3f | 2
16/11/2023 | Research | Myself | Research on SonarQube | Explained steps and compiled documentation for both the report and the group | 2
21/11/2023 | Coding Standards, Documentation | Myself | Modularization, Imports, Streamlit Widgets, Code Readability, Documentation Error Handling, Version Control, Testing, Dependency Management, Security, Style and Formatting | https://github.com/purpletechceo/purpletech-soen341projectF2023/wiki/Coding-Standards | 2
21/11/2023 | Continuous Integration, Documentation | Myself | Listed and explained all the steps included in the CI file works including pre-hook and continuous integration jobs, also modified the CI.yml so tests are executed first | https://github.com/purpletechceo/purpletech-soen341projectF2023/wiki/Continuous-Integration | 1.5
21/11/2023 | Static Testing, Documentation | Myself | Listed and explained all the steps needed to install and use SonarQube | https://github.com/purpletechceo/purpletech-soen341projectF2023/wiki/Static-Testing | 1.5
21/11/2023 | Unit Testing, Documentation | Myself | Listed and explained the following (providing an example) Unittest Usage Pytest Usage | https://github.com/purpletechceo/purpletech-soen341projectF2023/wiki/Unit-Testing | 1
26/11/2023 | Static Testing | Myself | SonarQube Report for Final Report | Locally installed dependencies, SonarQube, SonarQube's scanner, set up a project and ran report | 1
26/11/2023 | Meeting | Everyone | Project Finalization | Going over latest details with the group, mostly discussion on SonarQube (on my end) | 1
28/11/2023 | Documentation | Everyone | Final Report | Work on the following sections: Naming Convention, Continuous Integration, Static Testing, Appendix (Instructions and Report), 10 Problems Identification and Proposal of Potential Solutions | 3
|  |  |  | Total Hours | 27.5

## Shah
Shah's LOG
ID: 40176037
Program: COEN
PREP PHASE
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
2023-11-11 | Meeting | Everyone | Sprint 4 planning | Talked about the plan for Sprint 4 and task breakdown | 1.5
16/11/2023 | Meeting | Everyone | Presentation Preparation | Worked on all the Lessons Learned and Conclusion slides https://liveconcordia-my.sharepoint.com/:p:/g/personal/a_dicko_live_concordia_ca/EdNcecLv3ZBJoPRFStsQsX4B940z5rSSdh-aZ83IIgP8jg?e=OOtD3f | 2
SPRINT 4
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
2023-11-13 | Devlopment | Minh | Worked with Minh to finalize the embedding of the backend into the front end | Reformatted application so that it functions once embedded into the front end | 3
2021-11-21 | Meeting | Everyone | Discussion on Sprint 4 tasks, new information on presentation/report | Discussed presentation/project information provided by the professor, discussions on sonarqube, testings & documentation | 0.5
2023-11-25 | Meeting | Everyone | Follow up on task for Sprint 4 | Continued discussion from the last meeting and set action plans in motion. | 0.5
2023-11-26 | Developement | Myself | Integrated comparator and extra filters into the application, tested functionality | Completed and tested all functionalities working as inteneded | 3.5
2023-11-26 | Meeting | Everyone | Project finalization | Discussed overall github organization, made sure all issues were completed and the project was functioning as planned Feature Embedding + Presentation preparation | 1.5