## Overview
PurpleTech
Team Members
First Name | Last Name | ID | Program | Initials
Allaye | Dicko | 40224071 | SOEN | AD
Shah | Murshed | 40176037 | COEN | SM
Oyeyimika | Adeoye | 40124538 | COEN | OA
Huy | Min Le | 40209514 | COEN | HM
Sadee | Shadman | 40236919 | SOEN | SS
Grecia | O'Brien | 40236919 | SOEN | GO
ORGANIZATION STRUCTURE OF THIS SPREAD SHEET: |  |  |  |  | structure may alter as the course progresses and we see some aspect of the project require it's own category
Pre-Start: • Outlines any tasks or activities undertaken • May include training, early research etc. Sprint • Records activities conducted during the milestone.

## Summary
PREP PHASE
TYPE OF ACTIVITY | ACTIVITIES |  |  | OUTPUT | HOURS SPENT | [5 empty] | TOTAL | TEAM'S SIGNATURE
[5 empty] | Allaye | Shah | Oyeyimika | Minh | Sadee | Grecia |  | Allaye | Shah | Oyeyimika | Minh | Sadee | Grecia
Meeting and Brainstorm | 1) Kickoff Meeting : -Discussed roles and responsibilities. -Initiated GitHub repository setup. -Shared team members' backgrounds and skills. 2) PreliMinhary discussion on programMinhg languages and frameworks. -Task Allocation and Setup : -Defined individual roles and responsibilities. -Set up a dedicated team email address. -Started creating the GitHub repository. -Shared past experiences and backgrounds. |  |  | 1) Defined roles and responsibilities. 2) Set up a dedicated team email address. 3) Started creating the GitHub repository. | [5 empty] | N/A | 0
Research | 1) User Story Crafting - Collaboratively created user stories. 2) Ensured clarity and well-defined acceptance criteria. 3) Researched potential backend and frontend frameworks. 4) GitHub Functions Exploration - Explored GitHub functions for collaboration. - Provided feedback on potential uses for enhanced teamwork. - Researched GitHub capabilities. |  |  | 1) User stories with well-defined acceptance criteria. 2) Research findings on potential frameworks. | [5 empty] | N/A | 0
Miscellaneous | 1) Google Doc Collaboration -Enriched a shared Google Doc with project-related information. -Utilized the Google Doc as a central repository. -Shared information and updates among team members. 2) Documentation and Read Me File (September 21, 2023): - Updated the project's Read Me file. - Worked on general documentation efforts. - Ensured essential project details were accessible. |  |  | 1)Enriched Google Doc with project-related information. 2) Centralized repository for project data. 3) Updated Read Me file. 4) Progress in documentation efforts. | [5 empty] | N/A | 0
Meeting and Brainstorm | Distribution and Compledtion of Tasks. | [8 empty] | N/A | 0
[10 empty] | TOTAL | 0
SPRINT 1
TYPE OF ACTIVITY |  | ACTIVITIES | OUTPUT |  | HOURS SPENT | [5 empty] | TOTAL | TEAM'S SIGNATURE
[5 empty] | Allaye | Shah | Oyeyimika | Minh | Sadee | Grecia |  | Allaye | Shah | Oyeyimika | Minh | Sadee | Grecia
Meeting and Brainstorm |  | 1) README File: -Description of the Project -Team Members and Roles -Project Approach and Technology used 2) Document(s): -4 User Stories Backlog for Sprint 1 -Plan for the Next Sprint in a Wiki Page -Task Breakdown (derived from user stories, and assigned to a team member each of them). -Detailed Log of Each Team Member's Contribution including time spent for each activity -Meeting Minhutes Files | Completed all tasks and requirements

## Allaye
Allaye's LOG
ID: 40224071
PROGRAM:
PREP PHASE
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT | TEAM'S SIGNATURE
[6 empty] | Allaye | Shah | Oyeyimika | Min | Sadee | Grecia
2023-09-14 | Meeting/Brainstorming | Team | KickOff Meeting | 1) The team was created. 2) The GitHub setup was completed. 3) Project roles and responsibilities. 4) Discussion on best Framework. | 2
2023-09-21 | Meeting/Branstorming | Team | Sprint 1 Planning | 1. Discussed and outlined the specific requirements for the upcoming sprint. 2. Collaborated on a shared Google Doc to centralize project-related information. 3. Updated the README file for the project to enhance accessibility. 4. Task distribution their roles and strengths. | 3
2023-09-24 | Research | Myself | Research on what elements would be needed for the next sprint | A layout for writing the plan for sprint 2 in the wiki | 1
2023-09-26 | Meeting/Brainstorming | Team | Follow up on the distributed tasks | 1. Review of completed tasks, 2. Discussion on remaining work 3. Future plans on final review of the sprint before submission. | 2
SPRINT 1
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT | TEAM'S SIGNATURE
[6 empty] | Allaye | Shah | Oyeyimika | Min | Sadee | Grecia
2023-09-25 | Documentation/Reporting | Myself | Writing the wiki page that holds the plan for Sprint 2 | A complete wiki page with the required objetives, riksk and dependencies for Sprint 2 | 2
2023-09- | Publising | Myself | Writing the google sheet document that holds the taks distribution for Sprint 2 | A Google sheet that details the task distribution for sprint 2 with the risks and dependencies | 1

## Oyeyimika
Oyeyimika's LOG
ID: 40124538
PROGRAM:COEN
PREP PHASE
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT | TEAM'S SIGNATURE
[6 empty] | Allaye | Shah | Oyeyimika | Min | Sadee | Grecia
2023-09-14 | Meeting/Brainstorming | Team | KickOff Meeting | 1) The team was created. 2) The GitHub setup was completed. 3) Project roles and responsibilities. 4) Discussion on best Framework. | 2
2023-09-21 | Meeting/Branstorming | Team | Sprint 1 Planning | 1. Discussed and outlined the specific requirements for the upcoming sprint. 2. Collaborated on a shared Google Doc to centralize project-related information. 3. Updated the README file for the project to enhance accessibility. 4. Task distribution their roles and strengths. | 3
2023-09-22 | Documenting | Individually | 1. Recorded and documented meeting minutes for team meetings. 2. Managed the distribution of tasks for the sprint 1 among team members based on their roles and strengths. | 1. Organized and detailed meeting minutes for reference and documentation. 2. Everyone was successfully assigned a task. | 1
2023-09-26 | Meeting/Brainstorming | Team | Follow up on the distributed tasks | 1. Review of completed tasks, 2. Discussion on remaining work 3. Future plans on final review of the sprint before submission. | 2
2023-09-27 | Documenting | Individually | Maintained a log of activities, including hours spent on tasks and project-related work and familiarized more with Github. | 1. The team has an excel log detailing hours worked on different activities and tasks. 2. Pushed more documentations on github. | 2
2023-09-28 | Documenting | Individually | Documented Meeting minutes. | Pushed the information on Github | 1
2023-09- |  |  |  |  | 11
SPRINT 1
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT | TEAM'S SIGNATURE
[6 empty] | Allaye | Shah | Oyeyimika | Min | Sadee | Grecia
2023-09- | Documentation/Reporting | Individually | Created folders for the Sprint and Meeting Minutes, completed the documentations of the meeting minutes, log and task distribution | Completed my tasks and requirements | 1
2023-09- | Publising | Individually | Pushed all deliverables to github. | Pushed all deliverables to github. | 1
2023-09-

## Minh
Min's LOG
ID: 40209514
PROGRAM: COEN
PREP PHASE
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT | TEAM'S SIGNATURE
[6 empty] | Allaye | Shah | Oyeyimika | Minh | Sadee | Grecia
2023-09-14 | Meeting/Brainstorming | Team | KickOff Meeting | 1) The team was created. 2) The GitHub setup was completed. 3) Project roles and responsibilities. 4) Discussion on best Framework. | 2
2023-09-21 | Meeting/Branstorming | Team | Sprint 1 Planning | 1. Discussed and outlined the specific requirements for the upcoming sprint. 2. Collaborated on a shared Google Doc to centralize project-related information. 3. Updated the README file for the project to enhance accessibility. 4. Task distribution their roles and strengths. | 3
2023-09-26 | Meeting/Brainstorming | Team | Follow up on the distributed tasks | 1. Review of completed tasks, 2. Discussion on remaining work 3. Future plans on final review of the sprint before submission. | 2
2023-09- | Research
2023-09-
2023-09-
SPRINT 1
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
TEAM'S SIGNATURE
2023-09- | Documentation/Reporting | N/A | I wrote the readme file | I publish the readme on the github | 1h30 | Allaye | Shah | Oyeyimika | Minh | Sadee | Grecia
2023-09- | Reviewing | N/q | Double checking if everything is there and complete | updaded the change on the website | 30
2023-09-

## Sadee
Sadee's LOG
ID: 40236919
PROGRAM: SOEN
PREP PHASE
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT | TEAM'S SIGNATURE
[6 empty] | Allaye | Shah | Oyeyimika | Min | Sadee | Grecia
2023-09-14 | Meeting/Brainstorming | Team | KickOff Meeting | 1) The team was created. 2) The GitHub setup was completed. 3) Project roles and responsibilities. 4) Discussion on best Framework. | 2
2023-09-21 | Meeting/Branstorming | Team | Sprint 1 Planning | 1. Discussed and outlined the specific requirements for the upcoming sprint. 2. Collaborated on a shared Google Doc to centralize project-related information. 3. Updated the README file for the project to enhance accessibility. 4. Task distribution their roles and strengths. | 3
2023-09-26 | Meeting/Brainstorming | Team | Follow up on the distributed tasks | 1. Review of completed tasks, 2. Discussion on remaining work 3. Future plans on final review of the sprint before submission. | 2
2023-09-23 | Meeting | Shah Murshed | Meeting with Shah discussing and deciding on the format for the user stories | Generation of a loose template for the user stories | 30 minutes
2023-09-24 | Review | Shah Murshed | Reviewing userstories prior to presenting to rest of the team | Minor changes to written User stories | 21 minutes
SPRINT 1
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT | TEAM'S SIGNATURE
[6 empty] | Allaye | Shah | Oyeyimika | Min | Sadee | Grecia
2023-09-24 | Documentation/Reporting | Shah Murshed | Wrote and reviewed potential User stories |  | 1
2023-09-27 | Publising | Shah Murshed | Pushed personal deliverables to git hub |  | 21 minutes

## Grecia
Grecia's LOG
ID:
PROGRAM: SOEN
PREP PHASE
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT | TEAM'S SIGNATURE
[6 empty] | Allaye | Shah | Oyeyimika | Min | Sadee | Grecia
2023-09-26 | Meeting/Brainstorming | Team | Followed up with team directives. | 1. Reviewed of completed tasks. 2. Discussion on remaining work. 3. Future plans on final review of the sprint before submission. | 2
2023-09-26 | Agile Methodology | Myself | Carried out research on agile methodology, user story points, retrospectives and other tools. | 1. Reviewed all corresponding class material. 2. Started Agile crash course on Udemy. | 1.5
2023-09-26 | Back-End Technology | Myself | Carry out research in different back-end technologies for the project. | 1. Acquired technical knowledge prior to team meetings, became familiar with the different pros and cons of various frameworks. | 2
SPRINT 1
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
2023-09-26 | Documentation/Reporting | Myself | Spent time reading on the different features available on GitHub. | 1. Created Agile project board on GitHub 2. Added product backlog, sprint, done, in review, done columns amongst others. 3. Added labels, started to modify them to facilitate easy identification of tasks. 4. Explained to the new team the new functionalities added to the project repository. | 2
TEAM'S SIGNATURE
2023-09-26 | Wiki | Myself | Spent time reading GitHub documentation with respect to the Wiki functionality. | 1. Created graphics to add visual elements to the Wiki. 2. Added linked and organized content when needed. | 1
2023-09-26

## Shah
Shah's LOG
ID: 40176037
Program: COEN
PREP PHASE
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
2023-09-22 | Research | N/A | Researched frameworks for qualitative assessment | Notes which were used to write framework qualitative assesment, better understanding of markdown | 25 minutes
2023-09-23 | Meeting | Sadee Shadman | Meeting with Sadee discussing and deciding on the format for the user stories | Generation of a loose template for the user stories | 30 minutes
2023-09-24 | Review | Sadee Shadman | Reviewing userstories prior to presenting to rest of the team | Minor changes to written User stories | 21 minutes
SPRINT 1
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
2023-09-23 | Documentation/Reporting | N/A | Wrote the qualitative assesment based on written notes post research |  | 40 minutes
2023-09-24 | Documentation/Reporting | Sadee Shadman | Wrote and reviewed potential User stories |  | 1 hour
2023-09-27 | Publishing | Sadee Shadman | Pushed personal deliverables to git hub |  | 21 minutes