## Overview
PurpleTech
Team Members
First Name | Last Name | ID | Program | Initials
Allaye | Dicko | 40224071 | SOEN | AD
Shah | Murshed | 40176037 | COEN | SM
Oyeyimika | Adeoye | 40124538 | COEN | OA
Huy | Minh Le | 40209514 | COEN | HM
Sadee | Shadman | 40236919 | SOEN | SS
Grecia | O'Brien | 25372232 | SOEN | GO
ORGANIZATION STRUCTURE OF THIS SPREAD SHEET: |  |  |  |  | structure may alter as the course progresses and we see some aspect of the project require it's own category
Pre-Start: • Outlines any tasks or activities undertaken • May include training, early research etc. Sprint • Records activities conducted during the milestone.

## Allaye
Allaye's LOG
ID: 40224071
PROGRAM: SOEN
PREP PHASE
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
6/11/2023 | Meeting | Everyone | Sprint 3 planning | Talked about the plan for Sprint 3 and task breakdown | 1.5
SPRINT 3
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
2023-09-11 | Development | Myself | Integration | Integrated all feature into the final application and ensured functionality | 2.5
2023-09-11 | Development | Myself | Bug fixes | Added missing functionality and refactored code and labels, pushed final demo to github and had all members review | 3
8/11/2023 | meeting | Shah | Broker Display | Minh presented broker display UI approach. Feedback given to enhance user experience. Updated version to be provided for review. | 1
7/11/2023 | meeting | Yimika | Keyword search | Discussed code architecture and workflow with yimika regarding the keyword search and the display | 1

## Oyeyimika
Oyeyimika's LOG
ID: 40124538
PROGRAM:COEN
PREP PHASE
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT | TEAM'S SIGNATURE
[6 empty] | Allaye | Shah | Oyeyimika | Min | Sadee | Grecia
2023-11-02 | Documentation | Individual | -Documented tasks and requirements for Sprint 3 |  | 1
SPRINT 3
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT | TEAM'S SIGNATURE
[6 empty] | Allaye | Shah | Oyeyimika | Min | Sadee | Grecia
2023-11-02 | Meeting | Team | -Task breakdown and assigning user stories | Each member was assigned a task to implement until the next meeting | 1.5
11/07/2023 | Meeting | Shah | -Keyword search | Discussed code architecture and workflow with yimika regarding the keyword search and the display | 1
2023-11-08 | Coding | Individual | -Implement broker's display based on ground code, added more features and descriptions based on the tasks | -Completed the features and confirmed with Shah. | 2.5
1900-11-10 | Documentation | Individual | -Meeting Minutes | -Completed the documentation, created templates for the meeting minutes | 2.5
2023-11-10 | Miscellaneous | Individual | - General Sprint Overview, Pushing work to Github, filling required forms/blogs | -Ensuring proper use of github, all documents are done in readiness for submission. | 1.5

## Minh
Minh's LOG
ID: 40209514
PROGRAM: COEN
PREP PHASE
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
SPRINT 3
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
31/10/2023 | Coding | Myself | implementation of a map | added marker on the map where its link to diffrent address | 2
5/11/2023 | Research, Coding | Myself | work on the backend for the list of broker | reformat and change the layout added new variables and more details | 2.5
8/11/2023 | meeting | me/shah | Broker Display | Minh presented broker display UI approach. Feedback given to enhance user experience. Updated version to be provided for review. | 1
2023-09-11 | Testing, coding | Myself | redesign the front end added a new login button | designing the login page make it look more professional | 1.5
2023-10-11 | coding | myself | finalizing the color scheme for are website | added some color that would match are logo | 1.5
2023-08-11 | Evaluation | myself | Peer evaluation | sunbmited the form | 0.5

## Sadee
Sadee's LOG
ID: 40236919
PROGRAM: SOEN
PREP PHASE
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
SPRINT 3
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
2023-08-11 | Research + Coding + Testing | Myself | Implemention of submit an offer | Form created to submit offer, address autofilled, data saved to external text file and displayed | 6
2023-08-11 | Meeting | Everyone | General team meeting for updates | Showcased work to date, and also showed the team how to use Git, GitHub for Desktop to faciliate cloning, updates, and merging | 1.5
2023-11-11 | Evaluation | Myself | Peer Evaluation | Submitted | 0.2
2023-11-11 | Documentation | Myself | Acceptance Tests (AT) | Written 2 Acceptance Tests for each User Story 5 and 6 and linked to User Story-Tasks | 1

## Grecia
Grecia's LOG
ID: 25372232
PROGRAM: SOEN
PREP PHASE
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
SPRINT 3
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
2023-05-11 | Coding | Myself | Implement and test a mortgage calculator | The calculator was created and tested, ready for implementation, work contained in mortgageCalculator.py | 2.5
6/11/2023 | Research, Coding | Myself | Research on potential new small improvements for the application, started coding the following: leftside Bar filter, Clear Filters button, Export to CSV, Google maps display | Partial implementation, included in additionalFeatures.py (awaiting group discussion) | 3
2023-09-11 | Testing | Myself | Testing | Testing files | 1
2023-10-11 | Evaluation | Myself | Peer evaluation | Peer evaluation form completed and submitted for all peers in the group | 0.5
2023-08-11 | Meeting | Everyone | General team meeting for updates | Showcased work to date, and also showed the team how to use Git, GitHub for Desktop to faciliate cloning, updates, and merging | 1.5

## Shah
Shah's LOG
ID: 40176037
Program: COEN
PREP PHASE
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
6/11/2023 | Development | Myself | Foundation Code | Wrote foundation broker search code page woth the barebones functionality to streamline development process | 1.5
SPRINT 3
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
2023-09-11 | Development | Myself | Integration | Integrated all feature into the final application and ensured functionality | 2.5
2023-09-11 | Development | Myself | Bug fixes | Added missing functionality and refactored code and labels, pushed final demo to github and had all members review | 2.5
8/11/2023 | meeting | Minh | Broker Display | Minh presented broker display UI approach. Feedback given to enhance user experience. Updated version to be provided for review. | 1
7/11/2023 | meeting | Yimika | Keyword search | Discussed code architecture and workflow with yimika regarding the keyword search and the display | 1