## Overview
PurpleTech
Team Members
First Name | Last Name | ID | Program | Initials
Allaye | Dicko | 40224071 | SOEN | AD
Shah | Murshed | 40176037 | COEN | SM
Oyeyimika | Adeoye | 40124538 | COEN | OA
Huy | Min Le | 40209514 | COEN | HM
Sadee | Shadman | 40236919 | SOEN | SS
Grecia | O'Brien | 25372232 | SOEN | GO
ORGANIZATION STRUCTURE OF THIS SPREAD SHEET: |  |  |  |  | structure may alter as the course progresses and we see some aspect of the project require it's own category
Pre-Start: • Outlines any tasks or activities undertaken • May include training, early research etc. Sprint • Records activities conducted during the milestone.

## Allaye
Allaye's LOG
ID: 40224071
PROGRAM: SOEN
PREP PHASE
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
2023-10-15 | Meeting | Everyone | First meeting where the team organises themselves for the Sprint | - Detailed planning and assignment of core features and subtasks. - Discussion on writing comprehensive acceptance tests. - Progress review and issue deliberation for each core feature. - Clarifications on labeling of tests and tracking progress. - Clear plans for the upcoming follow-up meeting on October 21th | 1
SPRINT 2
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
2023-10-16 | Coding | Myself | Started implementing User Story 3(Property request visit) | A running code including a presentable page front and request form the user would fill and which answers would be used to create the request | 4
2023-10-21 | Meeting | Everyone | Progress Review | - Detailed planning and assignment of core features and subtasks. - Discussion on writing comprehensive acceptance tests. - Progress review and issue deliberation for each core feature. - Clarifications on labeling of tests and tracking progress. - Clear plans for the upcoming follow-up meeting on October 24th. | 1
2023-10-22 | Coding | Myself/Shah | Continued implementation of User story 3 + extra software to send confirmation emails to users | A finished running software where the user could submit a request, additional software where the brokers could see their requests and a bonus software to send confirmation emails to users when they submit a request | 6
2023-10-24 | Meeting | Everyone | Finishing touches + Discussion on presentation with product owner |  | 1
2023-10-25 | Coding/Documentation | Shah | data implementation to code + documentation | Addition to the implementation of .csv files to keep track of data and documentation for Sprint 2 planning and updating the wiki | 3

## Oyeyimika
Oyeyimika's LOG
ID: 40124538
PROGRAM:COEN
PREP PHASE
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT | TEAM'S SIGNATURE
[6 empty] | Allaye | Shah | Oyeyimika | Min | Sadee | Grecia
2023-10-15 | Meeting | TEAM | First meeting where the team organises themselves for the Sprint | - Detailed planning and assignment of core features and subtasks. - Discussion on writing comprehensive acceptance tests. - Progress review and issue deliberation for each core feature. - Clarifications on labeling of tests and tracking progress. - Clear plans for the upcoming follow-up meeting on October 21th | 1
SPRINT 2
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT | TEAM'S SIGNATURE
[6 empty] | Allaye | Shah | Oyeyimika | Min | Sadee | Grecia
2023-10-17 | Implementation of CRUDs on properties for brokers. | Individual | Implementation of user story 2- which is CRUDs properties for Brokers -Worked on Shah’s prototype for the app. -Added Create Updtate and delete features. | Completed 60% of tasks, encountered some errors with code. | 4
2023-10-21 | Meeting | TEAM | Progress Review | - Detailed planning and assignment of core features and subtasks. - Discussion on writing comprehensive acceptance tests. - Progress review and issue deliberation for each core feature. - Clarifications on labeling of tests and tracking progress. - Clear plans for the upcoming follow-up meeting on October 24th." | 1
2023-10-23 | Completion of assigned core feature | Sadee/ Shah | -Completion of assigned core feature - Worked on the database collection process, utilizing .csv files to store and manage data. - Discovered a way to link the administrator and brokers and send data from the brokers to the the administrator. | ‘-Brokers can efficiently manage their property listings. -Utilized .CSV files to facilitate data | 5
2023-10-24 | Meeting | Everyone | Finishing touches + Discussion on presentation with product owner |  | 1
2023-10-26 | Documenting Meeting Minutes | Individual | - Documented meeting minutes during project meetings. - Found a template and converted theinformation for all the meetings into it. | Comprehensive meeting minutes that capture the key discussions, decisions, and action items during the meeting. | 2

## Minh
Min's LOG
ID: 40209514
PROGRAM: COEN
PREP PHASE
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
2023-10-15 | Meeting | Everyone | First meeting where the team organises themselves for the Sprint | - Detailed planning and assignment of core features and subtasks. - Discussion on writing comprehensive acceptance tests. - Progress review and issue deliberation for each core feature. - Clarifications on labeling of tests and tracking progress. - Clear plans for the upcoming follow-up meeting on October 21th | 1
SPRINT 2
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
2023-10-24 | meeting | minh/ shah | getting the log in back end code | installing all the program needed to make the back end code work | 1
2023-10-24 | Front end / back end | alone | Embed log in page. | -We tested to see if the front end and back end will be able to merge together without having issues | 1
2023-10-28 | Front end | alone | working on the home page | - I implemented a map to be able to see the location of each properties. - Also redesign the home page to make it look more profesisonal - added new feature and navigation tab | 5

## Sadee
Sadee's LOG
ID: 40236919
PROGRAM: SOEN
PREP PHASE
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
2023-10-15 | Meeting | Everyone | First meeting where the team organises themselves for the Sprint | - Detailed planning and assignment of core features and subtasks. - Discussion on writing comprehensive acceptance tests. - Progress review and issue deliberation for each core feature. - Clarifications on labeling of tests and tracking progress. - Clear plans for the upcoming follow-up meeting on October 21th | 1
SPRINT 2
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
2023-10-13 | Meeting | Shah/Minh | " - Brief Discussion with Minh about the frontend - Detailed discussion with Shah about procedure with Streamlit and planning | - Complete understanding of Streamlit and progress planning - Having an outline of the Administrator page of the website | 1
2023-10-14 | Acceptance Tests (AT) | Myself | - Created a general format for writing the User Acceptance Tests - Wrote User Acceptance Tests for the 4 core features | Wrote 2 User Acceptance Tests for each core features without inputs, tests and output | 2
2023-10-21 | Meeting | Everyone | Progress Review | - Detailed planning and assignment of core features and subtasks. - Discussion on writing comprehensive acceptance tests. - Progress review and issue deliberation for each core feature. - Clarifications on labeling of tests and tracking progress. - Clear plans for the upcoming follow-up meeting on October 24th. | 1
2023-10-23 | Progress of assigned core feature | Oyeyimika/ Shah | - Worked on the database collection process, utilizing .csv files to store and manage data. - Discovered a way to link the administrator and brokers and send data from the brokers to the the administrator. | -Brokers can efficiently manage their property listings. -Utilized .CSV files to facilitate data | 4
2023-10-24 | Meeting | Everyone | Finishing touches + Discussion on presentation with product owner |  | 1
10/25/2023 10/26/2023 | Completion of assigned core feature | Myself | - Implementing the code for administrator CRUDS on own branch - Creating control operations for admins and linking them to main branch dataframe - Embedding the code with the main branch and testing for errors - Finishing up everything for final presentation | A finished running software with a new page for administrator CRUDs added on all properties listed by any brokers with relation to data on multiple .csv files | 7
2023-10-27 | Completing Acceptance Tests (AT) | Myself | All inputs, tests and outputs written and linked to User Story - Tasks on Wiki of Github | Acceptance Tests made available on wiki under User Stories - Tasks as required | 2

## Grecia
Grecia's LOG
ID: 25372232
PROGRAM: SOEN
PREP PHASE
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
2023-10-15 | Meeting | Everyone | First meeting where the team organises themselves for the Sprint | - Detailed planning and assignment of core features and subtasks. - Discussion on writing comprehensive acceptance tests. - Progress review and issue deliberation for each core feature. - Clarifications on labeling of tests and tracking progress. - Clear plans for the upcoming follow-up meeting on October 21th | 1
SPRINT 2
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
2023-10-21 | Meeting | Team | Present progress on testing to the team | Agreed on remaining of testing work | 1
2023-10-23 | Documentation Enhancement Continuous-integration Testing | Myself | Create Continuous Integration Workflow Using GitHub Actions | Implemented ci.yml which does the following: Step 1: Checks out the source code of the repository using the 'actions/checkout' action. Step 2: Updates the 'pip' package manager to the latest version using 'python -m pip install --upgrade pip.' Step 3: Installs project dependencies listed in 'requirements.txt' using 'pip install.' Step 4: Runs pytest on the specified test file 'Sprint 2/Implemented Features/Backend/test_initial.py.' Step 5: Runs pytest on the specified test file 'Sprint 2/Implemented Features/Backend/test_broker_visits.py.' Step 6: Runs pytest on the specified test file 'Sprint 2/Implemented Features/Backend/test_house_filtering.py.' | 3
2023-10-23 | Continuous-integration Coding Documentation Enhancement Testing | Myself | Create Initial (Empty) Unit Tests for the User Acceptance Tests | Code and implemented test_initial.py | 2
2023-10-23 | Continuous-integration Coding Documentation Enhancement Testing | Myself | Tests for the BrokerVisitsNotification.py implementation | Code and implemented test_broker_visits.py | 3
2023-10-23 | Continuous-integration Coding Documentation Enhancement Testing | Myself | Tests for the houseFilteringDemo.py implementation | Coded and implemented houseFilteringDemo.py | 3
2023-10-23 | Documentation | Myself | Include Testing Documentation on the Wiki | Added a page on the Wiki for Continous Integration | 2
2023-10-24 | Meeting | Team | Present progress on testing to the team | Documented work to later updated GitHub via issues | 1

## Shah
Shah's LOG
ID: 40176037
Program: COEN
PREP PHASE
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
2023-10-15 | Meeting | Everyone | First meeting where the team organises themselves for the Sprint | - Detailed planning and assignment of core features and subtasks. - Discussion on writing comprehensive acceptance tests. - Progress review and issue deliberation for each core feature. - Clarifications on labeling of tests and tracking progress. - Clear plans for the upcoming follow-up meeting on October 21th | 1
SPRINT 2
DATE | TYPE OF ACTIVITY | WORKED WITH | ACTIVITIES | OUTPUT | HOURS SPENT
2023-10-10 | Coding/Documentation | Myself | Wrote backbone code and created main branch | Wrote code which would serve as a foundation for rest of features, foundation included Aggridwith images and filtering with user login | 3
2023-10-13 | Meeting | Sadee/Minh | Collaboration with Minh and Sadee | Discussed embedding feature into frontend with Minh, outlined streamlit functionalities with Sadee | 1
2023-10-21 | Meeting | Everyone | Progress Review | - Detailed planning and assignment of core features and subtasks. - Discussion on writing comprehensive acceptance tests. - Progress review and issue deliberation for each core feature. - Clarifications on labeling of tests and tracking progress. - Clear plans for the upcoming follow-up meeting on October 24th. | 1
2023-10-22 | Coding | Allaye | Continued implementation of User story 3 + extra software to send confirmation emails to users | A finished running software where the user could submit a request, additional software where the brokers could see their requests and a bonus software to send confirmation emails to users when they submit a request | 1
2023-10-23 | Progress of assigned core feature | Oyeyimika/ Sadee | - Worked on the database collection process, utilizing .csv files to store and manage data. - Discovered a way to link the administrator and brokers and send data from the brokers to the the administrator. | -Brokers can efficiently manage their property listings. -Utilized .CSV files to facilitate data | 1
2023-10-24 | Coding | Minh | Embedding test into front end | Sucessfully integrated backend functionalities of login into front end made by Minh | 1
2023-10-24 | Coding | Allaye | Continued implementation of User story 3 + extra software to send confirmation emails to users | A finished running software where the user could submit a request, additional software where the brokers could see their requests and a bonus software to send confirmation emails to users when they submit a request | 1
2023-10-25 | Coding | Myself | Integrating all features in one webapplication | All features now work in conjunction with one another as a single webapp | 2
2023-10-24 | Meeting | Everyone | Finishing touches + Discussion on presentation with product owner |  | 1
2023-10-25 | Coding/Documentation | Allaye | data implementation to code + documentation | Addition to the implementation of .csv files to keep track of data and documentation for Sprint 2 planning and updating the wiki | 1